Custom Chatbot Front-End with Smartsheet & SharePoint via Claude API

Requirements overview — what's needed to move from Claude Projects to a custom-built chatbot

# 1. Why this is different from Claude Projects

The Smartsheet and SharePoint connections currently used inside the Claude Project (claude.ai) are a chat-UI-only feature. An API key does not inherit those connections — a custom front-end needs its own integration built from scratch, using the Claude API's tool-calling capability.

# 2. Two possible approaches

| Approach | How it works | Best for |
| --- | --- | --- |
| Direct tool use (recommended) | Backend calls the Smartsheet API and Microsoft Graph API (SharePoint) directly; Claude only decides which tool to call and with what arguments. | Teams building a fully custom app — most control, least moving parts. |
| MCP connector | Claude API connects to a remote MCP server (self-hosted or third-party) that wraps Smartsheet/SharePoint. | Teams that want to reuse an existing/maintained MCP server instead of writing API calls themselves. |

Recommendation: since a custom front-end is being built anyway, direct tool use is usually simpler — no separate server to host and maintain.

# 3. What's required — checklist

## 3.1 Anthropic / Claude API

- Anthropic API key (console.anthropic.com), billed separately from claude.ai Project usage.

- Decide on model (e.g., Claude Sonnet) and expected usage volume for cost planning.

- Familiarity with the Messages API and tool-use (function calling) format.

## 3.2 Smartsheet access

- Smartsheet API access token, generated from the Smartsheet Developer Portal.

- Decide which sheets/reports/workspaces the bot should be allowed to read or write — scope access accordingly.

- If using the MCP route: Smartsheet's official MCP server (open source) can be self-hosted and exposed over HTTPS.

## 3.3 SharePoint access

- An Azure AD (Entra ID) app registration with Microsoft Graph API permissions (e.g., Sites.Read.All, Files.Read.All, or write scopes if needed).

- OAuth 2.0 flow set up — either delegated (per-user login) or app-only (service account), depending on whether the bot should act as each user or as one shared identity.

- Decide which SharePoint sites/libraries/lists are in scope.

- No official Microsoft-published MCP server exists yet — this generally needs a thin custom wrapper around Microsoft Graph API either way.

## 3.4 Backend service (new build)

- A server (Node.js, Python, etc.) that: receives chat messages from the front-end, calls the Claude API, executes tool calls against Smartsheet/SharePoint, and returns results to Claude for a final answer.

- Secure storage for API keys and OAuth tokens/secrets (e.g., a secrets manager) — never in front-end code.

- Logging and error handling for failed API calls, rate limits, and auth expiry/refresh.

- Session/conversation state handling if multi-turn context needs to persist.

## 3.5 Front-end (new build)

- Chat UI (web app, Teams app, internal portal, etc.) that calls your backend, not the Claude API directly (keeps the API key server-side).

- Auth for your own users (e.g., SSO), separate from the Smartsheet/SharePoint service credentials.

- Design for how tool results (tables, documents, links) should render in the UI.

## 3.6 Security & governance

- Principle of least privilege: scope Smartsheet/SharePoint tokens to only the sheets/sites the bot needs.

- Review/approval process for what actions the bot can take automatically (read-only vs. write/update).

- Data handling review — confirm what conversation data is retained and where, per company policy.

- If evaluating a third-party MCP server instead of writing your own wrapper, vet its source and security practices before connecting it to company data.

# 4. Effort estimate by component

Scope: Phase 1 / MVP — single chatbot, two connectors, functional UI (not the polished card/diagram styling of a mature platform build).

| Component | What's involved | Rough effort |
| --- | --- | --- |
| Claude API integration | API key setup, Messages API calls, tool-use/function-calling schema design, prompt design & testing | 3–5 days |
| Smartsheet connector | Get API token, build backend functions to read/write sheets, map sheet data to tool schema, error handling | 3–5 days |
| SharePoint connector | Azure AD app registration, OAuth flow (delegated or app-only), Microsoft Graph API calls for sites/files/lists, error handling | 5–8 days (OAuth/Graph API is the fiddliest part) |
| Backend service | Server to orchestrate: receive chat → call Claude → call tools → return answer; session/state handling; secrets management | 5–7 days |
| Front-end (basic chat UI) | Chat interface, auth for your users (SSO), rendering plain text/table answers | 5–8 days (longer for polished cards/diagrams/citation pills) |
| Security/governance setup | Least-privilege token scoping, read vs. write permission decisions, data-retention policy check with your team | 2–3 days (mostly review/approval time) |
| Testing & hardening | Auth token refresh edge cases, rate limits, bad/missing data handling, user acceptance testing | 4–6 days |

Total for a working MVP: roughly 4–6 weeks for 1–2 engineers, assuming no major delays in Azure AD/Smartsheet admin approvals — that access-provisioning step is often the actual bottleneck, not the code.

## 4.1 What drives the estimate up or down

- Read-only vs. write access — read-only is simpler and safer to greenlight; write access adds review cycles and more careful error handling.

- Delegated (per-user) vs. app-only (service account) SharePoint auth — delegated is more secure/auditable but more complex to implement.

- How polished the UI needs to be — a functional internal tool vs. a fully styled experience (cards, diagrams, citation pills) can add a couple of extra weeks.

- Data volume — if a large-document RAG layer is needed later (vector store, embeddings, ingestion pipeline), that's a separate, bigger effort beyond this MVP scope.

# 5. Team needed

## 5.1 Minimum viable team (can ship in 4–6 weeks)

| Role | Count | Why |
| --- | --- | --- |
| Backend/API developer | 1 | Handles Claude API integration, tool-use schema design, Smartsheet + SharePoint connector logic, orchestration server. |
| Front-end developer | 1 | Chat UI, auth (SSO), rendering responses — can start part-time in week 1, ramp up once backend has stable endpoints. |
| DevOps / IT support (shared, not dedicated) | part-time | Azure AD app registration, secrets management setup, hosting/deployment — usually a few days total, not a full role. |

That's a true MVP team of 2 people. Many "separate" roles (e.g., "API developer" vs. "backend developer") are the same skill set at this scope — one person can own Claude API integration and both connectors, since it's all backend/orchestration work in the same codebase.

# 6. Suggested next step

A short technical spike is usually worthwhile before full build-out: stand up the backend with one working Smartsheet call and one working SharePoint call through Claude's tool-use format, end-to-end, before investing in the full front-end.